| WAYFINDER — THE QUIET FRONTIER Progress Snapshot • Batch N • 21 Oct 2026 | CURRENT STAGE M3 |
| --- | --- |

IN ONE WORD

M3

World Pipeline  —  In Progress  •  verified headless 278/278  •  Unity host & bake remaining

────────────────────────────────────────────────────────────────────────

Required status sentence  —  stages finished:{M0 Foundation — Unity 6.3 LTS project, URP, asmdefs, Bootstrap/Title scenes, input & build scripts (domain Verified headless; APK fix D-038 ready for rebuild) • M1 Vehicle proving ground — Scout S1 powertrain, fuel/damage/water/mud math Verified headless (WheelCollider/Cam in Unity is Implemented · parse-checked) • M2 Forest vertical slice — campaign session, atomic save/banking, exploration map, Q01–Q04 + hub travel & camp storage (Batches C/J) and M4 wiring — 20 missions, contracts, 20 research tiers, vehicles/items all Verified headless 278/278} and stages in progress:{M3 World pipeline — deterministic hash/PRNG, heightfield, seam checks, scatter placer & streaming planner Verified headless 164/164; WorldStreamer MonoBehaviour host, real-terrain scatter, full-mainland bake & route validation still to write/test on device} and stages yet to start:{M5 Content & assets — five biomes final art/audio & UI polish (placeholders in ASSET_MANIFEST.csv) • M6 Optimization & usability — 30/60 FPS, thermal, accessibility on Moto G45 • M7 Release candidate — clean builds, save migrations, airplane-mode suite & Play Store audit}

MILESTONE OVERVIEW  —  Source: first created file (Wayfinder_Production_Blueprint.txt v1.0, 14 Oct 2026 §21.2)

| Stage | Milestone (blueprint §21.2) | Quick description | Status today |
| --- | --- | --- | --- |
| M0 | Repository, pinned toolchain, boot/menu, device build, CI | Unity layout, URP, asmdefs, Bootstrap/Title, input actions, test assemblies, build scripts | Finished — Verified headless; APK installs on Moto G45; composite binding fix done (D-038), re-build pending to close gate |
| M1 | Physics proving ground, controls, camera, hazards | Scout S1 spec, WheelCollider, powertrain, camera, surfaces, fuel/damage, water/mud, winch, reset | Finished (math) — powertrain/fuel/damage/water math Verified 14 tests; WheelCollider/camera Implemented (needs Unity physics demo) |
| M2 | Forest vertical slice with complete loop | Slice 1 024 m, 6 landmarks, 12 caches, Q01–Q04, garage, 2 camp sockets, tiers 1–6, loop + save | Finished — Campaign Verified headless 278/278; map/reveal, supplies/selling, hub logistics & arbitrage fixed (Batches D/L/M); device 30-min playtest still required |
| M3 | World authoring / streaming pipeline & full mainland blockout | Deterministic hash/PRNG, heightfield, chunks, seams, route graph, streaming, scatter | IN PROGRESS — hash/PRNG/bitset, seam, scatter placer + streaming planner Verified (Batch G 164/164); WorldStreamer host, real-terrain bake, full-world traversal missing (KI-037/038) |
| M4 | Progression, all vehicles, items, missions, hubs | 4 vehicles, 20 tiers, 100 landmarks, 200 caches, 20 missions, contracts, camps, relics, finale | Finished (greybox) — content counts validated, DEF-003/004/007 wired, 23 sites in sites.json; needs greybox playthrough; contract sockets unplaced (KI-043) |
| M5 | Five-biome content and art/audio production | Final art, vehicle art, 5 regions, UI/icons, lore, sound, placeholder replacement | Not started — placeholders tracked; no hero assets claimed final |
| M6 | Optimization, accessibility, balance, localization readiness | Frame-time, memory, thermal, accessibility, economy pacing, quality tiers | Not started — quality tiers defined; simulator clean; no device profiles yet |
| M7 | External testing, platform preparation, release candidate | Clean builds, migrations, airplane-mode, legal/store audit, signed artifacts | Not started — build scripts ready; owner signing/authorization required |

EVIDENCE TODAY  —  what was actually executed (not claimed)

Headless C# (Roslyn 3.9, C#9, -warn:4): 0 warnings — 47 engine-free files + 30 Unity files syntax-checked — 278/278 EditMode tests PASS (Logs/headless/EditMode.headless.xml)

Content & formulas: validate_content.py PASS • formula_checks.py PASS (35 invariants) • economy_sim.py PASS (no deadlocks, no arbitrage) — 188/188 earlier, 278/278 now

Cloud build: Unity 6000.3.26f1 compiled 6 engine-free assemblies (15 Oct); last 3 runs failed on Input System 1.12.0 → repinned 1.20.1 & Editor asmdef fix; next dispatch now yields file/line annotations or APK

Device: Moto G45 APK installs & runs (M0 smoke gate); Steer composite binding InvalidOperationException fixed 20 Oct (D-038) — keyboard steering restored, touch OK — rebuild + 30-min slice playtest is next gate

Reference used: first created file — Wayfinder_Production_Blueprint.txt v1.0 (14 Oct 2026) + AI_IMPLEMENTATION_HANDOFF.txt — §21.2 Milestones table defines M0–M7. This report maps IMPLEMENTATION_STATUS.md (21 Oct, Batch M) against that table. Status values: Not started / In progress / Implemented / Verified / Blocked. ‘Verified’ means executed evidence exists.

NEXT  —  continuing the project →

1. Owner dispatches Android APK (free cloud build) → installs on Moto G45 → confirms no InvalidOperationException, WASD steering, Q01 end-to-end → commits packages-lock.json (KI-002) → M0 gate closes

2. Apply VehicleController.ApplyEffectiveStats seam (KI-025) so researched per-wheel grip/suspension reaches physics rig — dependency-ready without Unity

3. M3: implement WorldStreamer MonoBehaviour host, IScatterSurface baker, IMapTerrainSource, route graph + real terrain bake for VerticalSlice (KI-027/029/030/037/038)

4. M2 gate: 30-min on-device slice playtest (interruption/kill, 30 FPS) to prove save/atomicity in Unity — then M5 art sweep

Wayfinder  •  progress report  •  generated 21 Oct 2026 09:05   •  branch arena/5fb9f74d-wayfinder •  blueprint v1.0 §21.2 → IMPLEMENTATION_STATUS.md Batch N (21 Oct 2026)  •  headless 278/278 PASS